## Slide 1
Purchase to Pay is red and holds Gate 3; the other 11 sub-streams clear it
Northwind GBS - Project Meridian | Executive summary | Week 2026-W35
RED
7 of 12 sub-streams on track, 4 amber, 1 red. Gate 3 on 11 September is at risk.
Purchase to Pay
Country tax variants were underestimated at design; build slips past Gate 3 without additional Group Tax capacity. 52% complete.
Knowledge Transfer & Migration
Wave 1 started on time, but wave 2 and 3 now overlap by seven weeks and hub trainer capacity is the constraint. 44% complete.
Workflow & Intelligent Automation
Wave 1 is four automations behind because P2P design reopened; wave 2 scope is protected. 55% complete.
DECISIONS NEEDED
Approve the retention framework for 34 critical knowledge holders before selection opens
Confirm whether the German consultation timetable may run in parallel with Dutch selection
Release two additional Group Tax analysts to P2P through October
Accept a Gate 3 conditional pass for P2P, or move the gate for all of WP2
Northwind GBS - Project Meridian | Internal draft, not for distribution
1

## Slide 2
1
Where we stand
Work package status and the open RAID position

## Slide 3
1 of 4 work packages is red; the rest hold their gate dates
Work package status | Week 2026-W35 | Rated by worst sub-stream
1
AMBER
Operating Model & Service Design
70%
Works council consultation started two weeks late; selection window is now the binding constraint on Gate 4
Catalogue signed off in all five regions; focus moves to embedding SLAs in the service review
Both hubs contracted on plan; Krakow fit-out is the only remaining critical path item
Next: Krakow fit-out handover on 16 Oct
2
RED
Process Standardisation
63%
Country tax variants were underestimated at design; build slips past Gate 3 without additional Group Tax capacity
Legacy data quality is worse than assumed at design; cleansing needs three more stewards to hold the WP4 cut-off
Control framework on track for Gate 3; pilot close scheduled for the October cycle
Next: Control framework complete on 11 Sep
3
AMBER
Technology & Automation
58%
Wave 1 is four automations behind because P2P design reopened; wave 2 scope is protected
Template build completes into Gate 3; integration test scope agreed with all five regions
Design signed off against the KPI baseline; data layer build started on plan
Next: ERP template build complete on 11 Sep
4
AMBER
Transition & Change
48%
Wave 1 started on time, but wave 2 and 3 now overlap by seven weeks and hub trainer capacity is the constraint
Curriculum build tracking to plan; readiness index improving ahead of the wave 1 go-live
Next: Curriculum build complete on 23 Oct
Considerations
Group Tax capacity for P2P country variants (H, Marcus Adeyemi, due 04 Sep)
P2P country tax variants exceed design assumption (H, Chiara Bellandi, due 11 Sep)
Regional finance teams available for UAT (H, Daniel Okonkwo, due 25 Sep)
Hub trainer capacity constrains overlapping migration waves (H, Yusuf Demirci, due 05 Oct)
Northwind GBS - Project Meridian | Internal draft, not for distribution
3

## Slide 4
7 high-severity items are open, none yet past due
RAID log | Week 2026-W35 | 12 of 18 open items shown, most severe of each type
 | ID | Item | Owner | Due | Mitigation and next step
 | Risks (3) |  |  |  | 
H | R-01 | P2P country tax variants exceed design assumption | Chiara Bellandi | 11 Sep | Two Group Tax analysts released to P2P through October; conditional Gate 3 pass proposed for P2P only.
H | R-03 | Hub trainer capacity constrains overlapping migration waves | Yusuf Demirci | 05 Oct | Contract trainer capacity costed and put to the steering committee; resequencing wave 3 held as fallback.
H | R-04 | Legacy vendor data quality below the migration threshold | Anneke de Vries | 09 Oct | Three additional data stewards requested; automated duplicate detection brought forward.
 | Issues (3) |  |  |  | 
M | I-02 | Intercompany invoice routing design reopened | Chiara Bellandi | 18 Sep | Decision paper to the Global Process Owner forum on 2026-09-04.
M | I-04 | 128 incumbents not yet mapped to target roles | Tobias Lindqvist | 25 Sep | Regional HR leads to complete mapping ahead of consultation opening in each region.
M | I-01 | Wave 1 automation delivery four items behind plan | Sofia Marchetti | 02 Oct | Four automations proposed for wave 2; wave 1 benefit shortfall of 0.8 FTE accepted.
 | Dependencies (3) |  |  |  | 
H | D-01 | Group Tax capacity for P2P country variants | Marcus Adeyemi | 04 Sep | Steering committee decision requested; Group Tax lead has confirmed availability in principle.
H | D-03 | Master data cleansing cut-off gates migration validation | Anneke de Vries | 09 Oct | Cut-off protected by the additional steward request; partial-freeze option assessed as fallback.
M | D-04 | Information Security review of the automation platform | Sofia Marchetti | 30 Sep | Review slot confirmed for 2026-09-22; evidence pack submitted early.
 | Assumptions (3) |  |  |  | 
H | A-01 | Regional finance teams available for UAT | Daniel Okonkwo | 25 Sep | UAT scheduled around the close calendar; commitment to be confirmed at the September steering committee.
M | A-02 | Desk ratio of 1.4 holds for both hubs | Priya Raghunathan | 20 Nov | Ratio validated against the hybrid working policy; reviewed again at wave 2 planning.
M | A-04 | Benefit baseline holds at the FY26 cost base | Jonas Brenner | 18 Dec | Baseline frozen with Group Finance; any restatement to be handled as a change request.
Northwind GBS - Project Meridian | Internal draft, not for distribution
4

## Slide 5
2
Delivery plan
The roadmap and the gates it has to clear

## Slide 6
7 of 12 sub-streams complete into Gate 3; 5 do not
Programme roadmap | February 2026 to January 2027 | Position as at week 2026-W35
Work package
Sub-stream
Feb 26
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan 27
Operating Model & Service Design
Process Standardisation
Technology & Automation
Transition & Change
Service Catalogue & SLAs
Organisation & Role Design
Location & Footprint Strategy
Record to Report
Purchase to Pay
Order to Cash
Master Data & Controls
ERP Template Alignment
Workflow & Intelligent Automation
Reporting & Analytics
Knowledge Transfer & Migration
Change, Comms & Training
Service definition
SLA negotiation
Catalogue publication
Embed in service reviews
Role architecture
Structure & spans
Consultation & selection
Location assessment
Site selection & business case
Site build-out
Process design
Control framework build
Test & pilot close
Global rollout
Process design
Build & configuration
Test & UAT
Global rollout
Process design
Build & configuration
Test & UAT
Global rollout
Data model design
Cleansing & governance build
Migration validation
Template gap analysis
Template build
Integration test
Opportunity assessment
Automation build wave 1
Automation build wave 2
Reporting design
Data layer build
Dashboard build & UAT
Wave planning
Wave 1 knowledge transfer
Change impact assessment
Curriculum build
Delivery & readiness
Complete
In progress
Planned
At risk
Milestone
Reporting date
Considerations
Group Tax capacity for P2P country variants (H, Marcus Adeyemi, due 04 Sep)
P2P country tax variants exceed design assumption (H, Chiara Bellandi, due 11 Sep)
Regional finance teams available for UAT (H, Daniel Okonkwo, due 25 Sep)
Hub trainer capacity constrains overlapping migration waves (H, Yusuf Demirci, due 05 Oct)
Northwind GBS - Project Meridian | Internal draft, not for distribution
6

## Slide 7
Gate 3 on 11 September is at risk; the 2 gates behind it are passed
Stage gate criteria | Position as at week 2026-W35 (28 Aug 2026)
Gate 1: Mobilisation complete
13 Mar 2026 - passed
Characteristics:
Programme team mobilised and funded
Baseline scope and benefit case approved
Governance and cadence in place
Gate 2: Design sign-off
29 May 2026 - passed
Characteristics:
End-to-end process designs approved by all Global Process Owners
Target operating model and role architecture agreed
Design decision log closed or dispositioned
Gate 3: Build complete
11 Sep 2026 - at-risk
Characteristics:
ERP template build complete and unit tested
Control framework built and walked through with External Audit
P2P country tax variants configured
Wave 1 automations in pre-production
Gate 4: Go-live readiness
20 Nov 2026 - upcoming
Characteristics:
Integration and user acceptance testing signed off
Wave 1 knowledge transfer complete and stability review passed
Selection complete and hub roles appointed
Cutover and fallback plans rehearsed
Gate 5: Hypercare exit
22 Jan 2027 - upcoming
Characteristics:
All three waves live and stable for four consecutive weeks
SLAs met for two consecutive service review cycles
Benefit run-rate tracking within 10% of the case
Northwind GBS - Project Meridian | Internal draft, not for distribution
7

## Slide 8
3
Work packages
Charter and current position for each work package

## Slide 9
2 of 3 sub-streams are on track; Organisation & Role Design needs a decision this month
Work package 1 - Operating Model & Service Design | Charter and current position
1.1
Service Catalogue & SLAs
1.2
Organisation & Role Design
1.3
Location & Footprint Strategy
Key activities
Outcomes
Published catalogue v1.2 covering all 46 services with owner, SLA and unit cost
Closed the last four SLA exceptions with the Nordics and Brazil controllers
Agreed the KPI baseline set (14 measures) with Group Finance Policy
Ran the service-review dry run with the WP2 process owners
A costed catalogue of 46 services with agreed SLAs and a KPI baseline
78% complete, rated green at 2026-W35
Next: Service review cycle 1 run to the new SLAs on 13 Nov 2026
Completed role profiles for all 640 target roles and banded them with HR
Opened works council consultation in Germany and the Netherlands
Modelled three span-of-control scenarios for the hub leadership layer
Mapped 512 of 640 incumbents to target roles; 128 remain unresolved
Target structure, role profiles and span-of-control model for 640 GBS roles
61% complete, rated amber at 2026-W35
Next: Consultation concluded in all regions on 30 Oct 2026
Signed the Krakow lease; fit-out contractor mobilised on site
Closed the Kuala Lumpur headcount ramp plan with Workplace & Real Estate
Refreshed the footprint business case with actual salary benchmarks
Confirmed nearshore Bogota as the Americas coverage option
Confirm the two-hub-plus-nearshore footprint and secure the site build-out
72% complete, rated green at 2026-W35
Next: Krakow fit-out handover on 16 Oct 2026
Considerations
Works council consultation extends the selection window (H, Tobias Lindqvist, due 20 Nov)
128 incumbents not yet mapped to target roles (M, Tobias Lindqvist, due 25 Sep)
Krakow fit-out completion gates wave 1 onboarding (M, Priya Raghunathan, due 16 Oct)
Retention of critical knowledge holders through selection (M, Tobias Lindqvist, due 30 Oct)
Northwind GBS - Project Meridian | Internal draft, not for distribution
9

## Slide 10
2 of 4 sub-streams are on track; Purchase to Pay holds the critical path
Work package 2 - Process Standardisation | Charter and current position
2.1
Record to Report
2.2
Purchase to Pay
2.3
Order to Cash
2.4
Master Data & Controls
Key activities
Outcomes
Standardised the close calendar to a 5+2 day cycle across all five regions
Rebuilt the journal taxonomy; 214 entry types reduced to 61
Completed control design for the close cycle and walked it through with External Audit
Agreed the account reconciliation threshold policy with Internal Controls
One global close calendar, standard journal taxonomy and a rebuilt control set
74% complete, rated green at 2026-W35
Next: Control framework complete on 11 Sep 2026
Locked the three-way match tolerance policy across all regions
Reworked the invoice exception taxonomy after the tax logic finding
Rebuilt the Italy and Spain e-invoicing variants with Group Tax
Completed supplier master de-duplication design with WP2 Master Data
Single P2P flow with touchless invoice processing and one supplier master
52% complete, rated red at 2026-W35
Next: P2P build complete on 25 Sep 2026
Agreed a single dunning policy with the five regional credit committees
Designed the cash application matching rules with Treasury
Completed the billing consolidation design for the two legacy entities
Baselined DSO at 54 days as the benefit measurement start point
Standard billing, collections and cash application with one dunning policy
68% complete, rated green at 2026-W35
Next: O2C build complete on 25 Sep 2026
Published the governed data model for vendor, customer and chart of accounts
Profiled the legacy vendor master; 23% of records fail the new validation rules
Stood up the data stewardship model with named owners per domain
Agreed the cleansing cut-off date with WP4 migration planning
One governed master data model for vendor, customer and chart of accounts
57% complete, rated amber at 2026-W35
Next: Master data cleansing cut-off on 09 Oct 2026
Considerations
Group Tax capacity for P2P country variants (H, Marcus Adeyemi, due 04 Sep)
P2P country tax variants exceed design assumption (H, Chiara Bellandi, due 11 Sep)
Regional finance teams available for UAT (H, Daniel Okonkwo, due 25 Sep)
Legacy vendor data quality below the migration threshold (H, Anneke de Vries, due 09 Oct)
Northwind GBS - Project Meridian | Internal draft, not for distribution
10

## Slide 11
2 of 3 sub-streams are on track; Workflow & Intelligent Automation needs a decision this month
Work package 3 - Technology & Automation | Charter and current position
3.1
ERP Template Alignment
3.2
Workflow & Intelligent Automation
3.3
Reporting & Analytics
Key activities
Outcomes
Closed 96 of 118 template gaps; the remainder are localisation-only
Passed the Group IT Architecture design authority review
Completed the chart of accounts alignment with WP2 Master Data
Built the interface inventory for the 31 downstream systems
Collapse four regional ERP variants onto one global template
71% complete, rated green at 2026-W35
Next: ERP template build complete on 11 Sep 2026
Delivered 11 of 18 wave 1 automations into the pre-production environment
Passed the Information Security review for the document extraction service
Re-scoped four P2P automations pending the tax variant rework
Established the automation change-control process with the Automation CoE
Automate 38 candidate steps across P2P, O2C and R2R with a governed pipeline
55% complete, rated amber at 2026-W35
Next: Wave 1 automations in production on 02 Oct 2026
Signed off the reporting design against the WP1 KPI baseline
Built the cost-to-serve model down to service level
Stood up the data layer for SLA measurement in the test environment
Agreed the single source of truth for headcount with HR Organisation Design
One performance layer: SLA, KPI and cost-to-serve reporting for the service reviews
48% complete, rated green at 2026-W35
Next: Data layer live in test on 06 Nov 2026
Considerations
Information Security review of the automation platform (M, Sofia Marchetti, due 30 Sep)
Wave 1 automation delivery four items behind plan (M, Sofia Marchetti, due 02 Oct)
Single global cutover weekend leaves no fallback window (M, Rahul Menon, due 04 Dec)
Benefit baseline holds at the FY26 cost base (M, Jonas Brenner, due 18 Dec)
Northwind GBS - Project Meridian | Internal draft, not for distribution
11

## Slide 12
4
Governance
Who decides, who delivers, and who has to be consulted

## Slide 13
Decision rights sit with the steering committee; delivery sits with 4 work packages
Programme governance | Weekly programme board, Tuesday
Steering committee
Monthly, third Thursday
Helena Marchand - Chief Financial Officer
Arun Sethi - Group Financial Controller
Katrin Osei - Chief Human Resources Officer
Peer Wallenberg - Chief Information Officer
Maria Fontana - Regional CFO, Europe
Sam Okada - Regional CFO, Asia Pacific
Programme management
Weekly programme board, Tuesday
Nadia Bergström - Programme Director
Felix Aumann - Programme Manager
Grace Adeyinka - PMO Lead
Tomasz Wieczorek - Benefits & Reporting Lead
Ravi Balakrishnan - Risk & Assurance Lead
1
Operating Model & Service Design
CORE TEAM
GBS Design Office (8 FTE, dedicated)
Finance Operating Model (4 FTE, dedicated)
HR Organisation Design (2 FTE, 50% allocation)
CONTRIBUTING TEAMS
Group Finance Policy
Regional Controllers (5) (consulted per region)
Workplace & Real Estate
Legal & Employee Relations
2
Process Standardisation
CORE TEAM
Global Process Owners (4) (1 per E2E process)
Process Design Team (11 FTE, dedicated)
Internal Controls (3 FTE, dedicated)
CONTRIBUTING TEAMS
Regional Finance Teams (design workshops + UAT)
Group Tax (P2P and O2C tax logic)
Treasury (O2C cash application)
External Audit (control framework review)
3
Technology & Automation
CORE TEAM
ERP Template Team (9 FTE, dedicated)
Automation CoE (5 FTE, dedicated)
Data & Analytics (4 FTE, dedicated)
CONTRIBUTING TEAMS
Group IT Architecture (design authority)
Information Security (gated reviews)
Platform Vendor (statement of work)
Regional IT (5) (cutover support)
4
Transition & Change
CORE TEAM
Transition Management Office (6 FTE, dedicated)
Change & Communications (4 FTE, dedicated)
Training Design (3 FTE, dedicated)
CONTRIBUTING TEAMS
Retained Finance Leads (5) (wave sign-off)
Hub Operations Leadership
Legal & Employee Relations
Internal Communications
Comments
Steering committee meets monthly; two additional decision points are scheduled around Gate 3 and Gate 4.
Programme board reviews RAID weekly and escalates any high-severity item open beyond 14 days.
Work package leads hold delegated authority up to EUR 250k and one week of schedule float.
Regional CFOs sign off wave readiness for their own entities; the CFO signs the global go / no-go.
Northwind GBS - Project Meridian | Internal draft, not for distribution
13